## Sheet1
Date | Actual_Cumulative | Target_Cumulative | ADD | Registered Farm Households | District | Number of EPAs | Total sections | Sections done | Sections in progress | Sections not started | Total blocks | Blocks done | Completed blocks % | Blocks in progress | Blocks not started | District | N | Mean1 (Ha) | Mean2 (Ha) | Median (Ha) | Median (Ha)
15/07/2024 | 1254617 | 1260000 | LILONGWE | 470728 | Phalombe | 6 | 59 | 10 | 45 | 0 | 462 | 307 | 66.45% | 80 | 75 | BALAKA | 52569 | 0.65 | 0.35 | 0.29 | 0.4
16/07/2024 | 1358669 | 1350000 | MACHINGA | 365684 | Thyolo | 6 | 56 | 5 | 54 | 0 | 453 | 298 | 65.78% | 186 | 0 | BLANTYRE | 70085 | 0.43 | 0.26 | 0.22 | 0.4
17/07/2024 | 1462721 | 1440000 | BLANTYRE | 358493 | Mulanje | 5 | 57 | 4 | 49 | 4 | 423 | 294 | 69.5% | 29 | 140 | CHIKWAWA | 40779 | 0.75 | 0.4 | 0.32 | 0.61
18/07/2024 | 1566777 | 1530000 | KASUNGU | 276004 | Dowa west | 4 | 53 | 24 | 27 | 1 | 415 | 354 | 85.3% | 60 |  | CHIRADZULU | 40316 | 0.39 | 0.26 | 0.22 | 0.32
19/07/2024 | 1686409 | 1620000 | MZUZU | 139393 | Rumphi | 7 | 55 | 293 | 5 | 64 | 409 | 116 | 28.36% | 116 |  | CHITIPA | 28468 | 1.03 | 0.5 | 0.41 | 0.81
20/07/2024 | 1797722 | 1710000 | SALIMA | 78695 | Mzimba north | 9 | 73 | 43 | 21 | 7 | 575 | 473 | 82.26% | 57 | 50 | DEDZA | 89932 | 0.62 | 0.35 | 0.28 | 0.4
21/07/2024 | 1905043 | 1800000 | SHIRE VALLEY | 75977 | Likoma | 2 | 2 | 1 | 1 | 0 | 16 | 15 | 93.75% | 1 | 0 | DOWA EAST | 39759 | 1 | 0.49 | 0.38 | 0.81
22/07/2024 | 2019058 | 1890000 | KARONGA | 67639 | Chitipa | 6 | 56 | 29 | 23 | 4 | 448 | 348 | 77.68% | 62 | 39 | DOWA WEST | 32078 | 1.1 | 0.52 | 0.41 | 0.81
[5 empty] | Karonga | 6 | 53 | 30 | 17 | 6 | 424 | 315 | 74.29% | 59 | 109 | KARONGA | 32268 | 0.64 | 0.38 | 0.29 | 0.4
[5 empty] | Ntcheu | 7 | 87 | 21 | 49 | 17 | 627 | 367 | 58.53% | 230 | 30 | KASUNGU | 87967 | 1.23 | 0.56 | 0.45 | 1.01
[5 empty] | Dedza | 10 | 52 | 37 | 7 | 8 | 82 | 67 | 81.71% | 3 | 12 | LIKOMA | 1555 | 0.29 | 0.22 | 0.16 | 0.2
[5 empty] | Blantyre | 5 | 101 | 61 | 11 | 29 | 1174 | 755 | 64.31% | 69 | 350 | LILONGWE EAST | 108738 | 0.7 | 0.38 | 0.3 | 0.51
[16 empty] | LILONGWE WEST | 158342 | 0.82 | 0.43 | 0.35 | 0.61
[16 empty] | MACHINGA | 78061 | 0.5 | 0.29 | 0.23 | 0.4
[16 empty] | MANGOCHI | 129720 | 0.63 | 0.34 | 0.28 | 0.4
[16 empty] | MCHINJI | 47867 | 0.97 | 0.48 | 0.38 | 0.81
[16 empty] | MULANJE | 66514 | 0.41 | 0.27 | 0.22 | 0.36
[16 empty] | MWANZA | 15022 | 0.59 | 0.32 | 0.28 | 0.4
[16 empty] | MZIMBA NORTH | 35942 | 0.91 | 0.45 | 0.37 | 0.81
[16 empty] | MZIMBA SOUTH | 50833 | 0.97 | 0.48 | 0.38 | 0.81
[16 empty] | NENO | 10343 | 0.78 | 0.4 | 0.34 | 0.61
[16 empty] | NKHATABAY | 17851 | 0.86 | 0.45 | 0.37 | 0.69
[16 empty] | NKHOTAKOTA | 31294 | 0.77 | 0.41 | 0.34 | 0.61
[16 empty] | NSANJE | 22942 | 0.65 | 0.35 | 0.26 | 0.4
[16 empty] | NTCHEU | 64519 | 0.63 | 0.35 | 0.29 | 0.4
[16 empty] | NTCHISI | 37756 | 1.18 | 0.54 | 0.46 | 1.01
[16 empty] | PHALOMBE | 45008 | 0.56 | 0.33 | 0.24 | 0.4
[16 empty] | RUMPHI | 19252 | 1.01 | 0.51 | 0.41 | 0.81
[16 empty] | SALIMA | 39426 | 0.91 | 0.45 | 0.38 | 0.81
[16 empty] | THYOLO | 72773 | 0.37 | 0.24 | 0.21 | 0.28
[16 empty] | ZOMBA | 66860 | 0.47 | 0.29 | 0.23 | 0.4